## Executive Summary
Babysteps v45 — Implemented Requirements Gap Audit
Metric | Value |  | Audit basis | Repository | Branch | HEAD | Requirements | Audit type | Date
Requirements audited | 20 |  | Static code-to-frozen-contract comparison | SridharVoleti/babystepsindia | master | 517e3cf3ef141908679742ef2abb60dd93b32400 | Babysteps_Platform_Requirements_v45.xlsx | Behavior + architecture + integration gaps | 2026-08-08
Distinct gaps identified | 107
Critical gaps | 11
Requirements below 70% | 5
Weighted match | 74.57%
Requirement | Title | Match % | Stage | Confidence | Open gaps
IA-001 | Parent Registration & Login | 85% | Substantial | High | 4
IA-002 | Parent Profile Onboarding | 92.86% | Substantial | High | 3
IA-003 | Account Security & Lifecycle | 76.67% | Substantial | High | 5
LP-001 | Learner Profile Creation | 94.23% | Substantial | High | 3
LP-002 | Learner Profile Correction | 96% | Substantial | High | 3
LP-004 | Learner Selection & Active Session Control | 77.78% | Substantial / Regressed | High | 7
AR-001 | Canonical App Registry | 96.67% | Substantial | High | 3
AN-001 | Minimal-Data Daily Analytics | 94.29% | Substantial | High | 3
AR-002 | Automated App Deployment & Release Safety | 50% | Partial | Medium | 10
LA-001 | Secure Cross-Domain App Launch | 80% | Substantial / Partial Integration | Medium-High | 6
LA-002 | Session-Bound API Authorization | 72.5% | Substantial / Contract Gap | High | 6
LA-003 | Compact Progress Persistence | 80% | Substantial / Partial Amendments | Medium-High | 6
LA-004 | Session Completion & Technical Credit | 76.67% | Substantial / Regressed | Medium-High | 5
AU-001 | Central Authorization Policy | 84% | Substantial | High | 5
AU-002 | Parent/Learner Authorization Modes | 61.43% | Partial | High | 7
SC-001 | Browser-Local Session Runtime | 56.67% | Partial | High | 7
SC-002 | Standard Session Credits & Weekly Pacing | 78.75% | Substantial / Source Gap | High | 5
SC-003 | Atomic Session Start & Usable Launch | 70% | Partial | High | 5
EN-001 | Paid Cycle → Entitlement Materialization | 55% | Partial | High | 7
EN-002 | Effective App Access & Overlap Control | 48.75% | Partial | High | 7

## Requirement Match
Requirement ID | Requirement Title | Acceptance Criteria / Tests | Full Match | Partial Match | Missing / Contradicted | Weighted Points | Match % | Implementation Stage | Confidence | Key Gap Summary | Gap Count
IA-001 | Parent Registration & Login | 10 | 7 | 3 | 0 | 8.5 | 85% | Substantial | High | Core behavior works locally; production Supabase Auth/email delivery/shared rate-limit contract is not active. | 4
IA-002 | Parent Profile Onboarding | 14 | 12 | 2 | 0 | 13 | 92.86% | Substantial | High | Strong local match; remaining deductions are production Supabase/RLS and real invoice-delivery integration. | 3
IA-003 | Account Security & Lifecycle | 15 | 10 | 3 | 2 | 11.5 | 76.67% | Substantial | High | Raw email-change token is stored locally; Supabase email-change configuration and full session revocation are incomplete. | 5
LP-001 | Learner Profile Creation | 26 | 23 | 3 | 0 | 24.5 | 94.23% | Substantial | High | Core profile rules are strong; passkey-dependent paths, production RLS and billing integration are not end-to-end. | 3
LP-002 | Learner Profile Correction | 25 | 23 | 2 | 0 | 24 | 96% | Substantial | High | Core update/version/idempotency behavior is strong; commercial/session integration is not production-complete. | 3
LP-004 | Learner Selection & Active Session Control | 45 | 32 | 6 | 7 | 35 | 77.78% | Substantial / Regressed | High | Latest v45 removes repeated-interruption auto-completion, but code still supports it; browser-runtime/passkey gaps remain. | 7
AR-001 | Canonical App Registry | 30 | 28 | 2 | 0 | 29 | 96.67% | Substantial | High | Registry lifecycle is strong; production Supabase/RLS and billing-side remediation integration remain. | 3
AN-001 | Minimal-Data Daily Analytics | 35 | 32 | 2 | 1 | 33 | 94.29% | Substantial | High | Analytics design is strong; production scheduler/service identity and runtime-store deployment are incomplete. | 3
AR-002 | Automated App Deployment & Release Safety | 44 | 17 | 10 | 17 | 22 | 50% | Partial | Medium | Deployment primitives exist, but provider discovery, CI provenance, immutable promotion, compatibility and rollback automation are incomplete. | 10
LA-001 | Secure Cross-Domain App Launch | 40 | 29 | 6 | 5 | 32 | 80% | Substantial / Partial Integration | Medium-High | Launch flow exists; machine identity is shared-secret based and SC-003 provisional launch + full cross-domain production integration are incomplete. | 6
LA-002 | Session-Bound API Authorization | 40 | 25 | 8 | 7 | 29 | 72.5% | Substantial / Contract Gap | High | Short-lived EdDSA access token is strong, but starting sessions incorrectly receive an active broad-scope grant instead of provisional usable-launch-only grant. | 6
LA-003 | Compact Progress Persistence | 40 | 29 | 6 | 5 | 32 | 80% | Substantial / Partial Amendments | Medium-High | Core current-row/versioned progress is present; newer progress migration/recovery/summary amendments are not fully implemented. | 6
LA-004 | Session Completion & Technical Credit | 60 | 42 | 8 | 10 | 46 | 76.67% | Substantial / Regressed | Medium-High | Completion/credit mechanics are substantial; repeated-interruption behavior and newer local-progress integration diverge from v45. | 5
AU-001 | Central Authorization Policy | 50 | 39 | 6 | 5 | 42 | 84% | Substantial | High | Canonical action/policy layer exists; machine identity, distributed runtime and deployment-provider authorization remain incomplete. | 5
AU-002 | Parent/Learner Authorization Modes | 35 | 18 | 7 | 10 | 21.5 | 61.43% | Partial | High | Mode isolation/context code exists, but no WebAuthn passkey implementation proves learner unlock; caller supplies a boolean passkeyVerified. | 7
SC-001 | Browser-Local Session Runtime | 30 | 14 | 6 | 10 | 17 | 56.67% | Partial | High | Central server contracts exist, but the required IndexedDB/Web Locks/BroadcastChannel learning-app runtime is not implemented here; old interruption rule remains. | 7
SC-002 | Standard Session Credits & Weekly Pacing | 40 | 29 | 5 | 6 | 31.5 | 78.75% | Substantial / Source Gap | High | Credit batches/pacing exist; allocation source is not a verified billing event and rollover expiry can drift across short months. | 5
SC-003 | Atomic Session Start & Usable Launch | 35 | 22 | 5 | 8 | 24.5 | 70% | Partial | High | Reservation/start flow exists, but provisional LA-002 grant, real browser runtime-ready handshake, AU-004 identity and PR migration gate are incomplete. | 5
EN-001 | Paid Cycle → Entitlement Materialization | 40 | 18 | 8 | 14 | 22 | 55% | Partial | High | Service explicitly accepts caller-supplied paid-cycle/app snapshot because billing producer/catalog do not exist; grace/cancellation overlays are omitted. | 7
EN-002 | Effective App Access & Overlap Control | 40 | 16 | 7 | 17 | 19.5 | 48.75% | Partial | High | Period overlap/effective state exists; checkout/payment lifecycle, grace/cancellation and resume-across-paid-end behavior do not match v45. | 7

## Gap Register
Gap ID | Requirement ID | Severity | Category | Acceptance / Rule | Gap Description | Evidence / Reason | Recommended Fix | Code Evidence URL | Requirements Source | Status | Resolution Notes
GAP-001 | IA-001 | High | Production runtime | AC1-AC7 / runtime contract | Production identity path is not Supabase Auth. | README states current runtime is local SQLite + built-in session auth; Supabase helpers/migrations are dormant. | Implement and activate SupabaseAuthAdapter in production, preserving stable parent IDs and current adapter contract. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires activating Supabase Auth in production (current runtime is local SQLite + built-in session auth by design, see README).
GAP-002 | IA-001 | Medium | Email delivery | AC3, AC7 | Verification/reset delivery is a development URL rather than configured production email delivery. | Server actions return verificationUrl/resetUrl for local development. | Wire Supabase/custom SMTP templates and callbacks; never expose verification/reset links in production UI responses. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/app/(auth)/actions.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires configuring production email delivery (Supabase/custom SMTP callbacks); same root cause as GAP-001/004.
GAP-003 | IA-001 | Medium | Rate limiting | Security/NFR | Rate limiter is process-local and will not enforce limits consistently across multiple Vercel instances. | README describes in-memory fixed-window rate limiting as single-process only. | Move auth rate limits to a shared durable store or provider-native rate limiter before scale-out. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a shared durable store (Redis/Vercel KV) for cross-instance rate limiting; current in-memory limiter is correct for single-process.
GAP-004 | IA-001 | Medium | Production verification | AC3-AC9 | Production Supabase session/email-verification behavior is not exercised end-to-end. | Current tests primarily validate the SQLite adapter and local cookie flow. | Add Supabase integration/E2E tests for signup, verify, reset, suspended/deleted gating and recovery upsert. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a live Supabase project to exercise production auth/session/email flows end-to-end.
GAP-005 | IA-002 | Medium | Production runtime | AC1-AC14 | Parent onboarding runs on the local SQLite/auth stack rather than the frozen Supabase production stack. | README marks Supabase production path dormant. | Port transactional profile+consent update to Supabase/Postgres and validate RLS/authorization. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires porting parent onboarding to the production Supabase/Postgres stack.
GAP-006 | IA-002 | Low | Billing integration | AC11-AC12 | Invoice recipient/delivery behavior is implemented as local metadata utility, not proven against a real billing/invoice provider. | Identity code can compute labels, but BI billing requirements/providers are not implemented. | Integrate the label/email contract with the billing/invoice producer and add contract tests. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a real billing/invoice provider (BI requirements not yet built).
GAP-007 | IA-002 | Medium | Authorization/RLS | Security | Production row-level protection of phone/profile data is not demonstrated. | Current runtime relies on application guards over SQLite. | Implement Supabase RLS policies and integration tests for parent/support/admin read boundaries. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires Supabase RLS policies on a live Postgres project.
GAP-008 | IA-003 | Critical | Credential security | AC15 | Email-change verification token is stored raw in a platform table. | requestEmailChange inserts token directly into email_change_requests; resend also replaces the raw token. | Use provider-managed token/nonce or store only a one-way hash; never persist the raw verification token. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/db/account-security-repo.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: email-change verification token is now sha256-hashed (token_hash column) - raw token never persisted. src/lib/db/account-security-repo.ts, src/lib/db/schema.sql.
GAP-009 | IA-003 | High | Supabase configuration | AC4-AC8 | Secure Email Change / 86,400-second Supabase email-link expiry is not configured in the active runtime. | Code comment explicitly says equivalent Supabase Auth project setting still needs configuring. | Configure Supabase Auth exactly as frozen and add deployment/configuration assertions. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/db/account-security-repo.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires configuring Supabase Auth project settings (email-link expiry) directly.
GAP-010 | IA-003 | High | Session revocation | AC11 | Soft delete does not explicitly atomically revoke every learner session and app grant in the shown transaction. | softDeleteAccount updates profile and learner unlock contexts; no direct learner_sessions/app_session_grants revocation appears in that transaction. | Add authoritative transactional revocation of parent sessions, learner sessions, launch state and app grants. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/db/account-security-repo.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: softDeleteAccount now atomically revokes every active/starting learner session and its app grant via new revokeActiveLearnerSessionsForParent, in the same transaction. src/lib/learning-session/gateway.ts, src/lib/db/account-security-repo.ts.
GAP-011 | IA-003 | Medium | Privacy logging | Security / AC15 | Email-change account-event metadata stores old/new email values. | finalizeEmailChange records oldEmail/newEmail in account_events metadata. | Store minimized identifiers/change type only; mask or omit raw email values from routine audit/log payloads. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/db/account-security-repo.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: account_events for email_change_requested/verified now store maskEmail() output, not raw addresses (parent_email_history keeps the full archival record per its own append-only rule). src/lib/db/account-security-repo.ts.
GAP-012 | IA-003 | Medium | Provider callback hardening | AC4-AC8, AC14 | Local token callback does not prove the full Supabase email_change token type/origin contract. | Current implementation uses a locally generated token and local user-email mutation. | Use Supabase callback verification, token type/origin checks and reconciliation tests in production. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/db/account-security-repo.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires Supabase's own email-change callback/token verification.
GAP-013 | LP-001 | Medium | Production data security | Security / isolation | Learner creation/isolation is not validated under production Supabase RLS. | Current learner repo/tests run against SQLite. | Implement learner RLS policies and multi-parent integration tests on Supabase. | https://github.com/SridharVoleti/babystepsindia/blob/master/tests/learner-profile.test.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires Supabase RLS to validate learner isolation on production Postgres.
GAP-014 | LP-001 | Medium | Passkey dependency | AT-LP-001-22 / IA-004 dependency | Passkey-dependent learner-lock path cannot be fully satisfied because IA-004 WebAuthn is not implemented. | Authorization mode tables exist but no WebAuthn credential/challenge verification implementation was found. | Implement IA-004 before certifying learner app/passkey locking acceptance tests. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/authorization/modes.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - IA-004 WebAuthn built (src/lib/webauthn/service.ts); real passkey registration/authentication now backs the learner-lock trust boundary, closing the dependency.
GAP-015 | LP-001 | Low | Commercial integration | Integration | No-subscription/no-app-state-on-create behavior is only proven against local placeholder commercial tables. | Billing requirements/providers are absent from the repository implementation. | Add integration tests against the eventual BI/EN production services to prove learner creation has no commercial side effects. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires the BI/EN billing services this depends on to exist.
GAP-016 | LP-002 | Medium | Production data security | AT-LP-002-22/23 | GET/PATCH isolation is not proven with Supabase RLS. | Route is guarded in application code; production database policy path is dormant. | Add RLS and API integration tests against Supabase. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/app/v1/learners/[learnerId]/route.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires Supabase RLS on a live Postgres project.
GAP-017 | LP-002 | Medium | Billing integration | AT-LP-002-09 | Commercial-state preservation is not end-to-end against implemented billing/subscription lifecycle. | BI-001..BI-005 are absent; current tests can only preserve local placeholder rows. | Re-run correction regression suite after billing is implemented, asserting immutable subscription/entitlement rows. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/app/v1/learners/[learnerId]/route.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires the BI billing/subscription lifecycle to exist.
GAP-018 | LP-002 | Low | Session integration | AT-LP-002-07/10 | DOB-next-session snapshot and weekly-use preservation depend on session flows that still have v45 mismatches. | LP-004/SC-003 are not fully aligned with v45. | Add cross-requirement integration tests once session start/runtime gaps are fixed. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/app/v1/learners/[learnerId]/route.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - added cross-requirement integration tests (tests/gap-018-lp002-session-integration.test.ts) covering a date-of-birth change against weekly session-slot usage and analytics age-band attribution across the full session lifecycle.
GAP-019 | LP-004 | Critical | Requirement regression | AT-LP-004-37 | Code still supports automatic completion after repeated interruption, but v45 requires that rule to be absent. | finalizeSessionAutomatically accepts repeated_interruption_after_threshold. | Remove repeated-interruption auto-completion; hard expiry should be the recovery boundary. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/session-finalization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: removed the repeated_interruption_after_threshold auto-completion path entirely - hard expiry is the sole recovery boundary now. src/lib/session-finalization/service.ts, src/lib/learning-session/gateway.ts.
GAP-020 | LP-004 | High | Browser runtime | AT-LP-004-36 | Required one-owner-tab browser runtime control is not implemented in the central repository. | No actual Web Locks/BroadcastChannel ownership runtime was found. | Ship the learning-app runtime SDK/implementation and test same-origin multi-tab ownership. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001 browser runtime SDK built (src/lib/session-runtime-sdk/): real IndexedDB-backed runtime with Web Locks + BroadcastChannel single-owner-tab coordination.
GAP-021 | LP-004 | High | Local persistence | AT-LP-004-38 | Meaningful local runtime checkpoints are not implemented end-to-end in a learning app. | Central progress APIs exist, but the browser-local change-gated runtime layer is absent. | Implement SC-001 runtime state and only persist at meaningful boundaries. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001 browser runtime SDK: real IndexedDB persistence via createRuntime/recordMeaningfulChange, only writing at meaningful boundaries.
GAP-022 | LP-004 | High | Safety checkpoint | AT-LP-004-39 | Five-minute change-gated safety checkpoint behavior is not implemented in the browser runtime. | No learning-app runtime timer/checkpoint SDK is present. | Add change-gated five-minute checkpoint logic to SC-001 SDK with deterministic clock tests. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001 browser runtime SDK: checkpointIfDue implements the five-minute change-gated safety checkpoint with deterministic clock tests.
GAP-023 | LP-004 | High | Learner authentication | Selection/start gates | Learner mode is not cryptographically unlocked by WebAuthn. | AU-002 accepts a caller-provided passkeyVerified boolean; IA-004 implementation is absent. | Implement IA-004 and require verified learner-mode context before learner home/start. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/authorization/modes.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - IA-004 WebAuthn cryptographically unlocks learner mode via activateLearnerMode's one-time verificationReceiptId, consumed only after a real passkey assertion verifies (recordTrustedPasskeyVerification).
GAP-024 | LP-004 | Medium | Schedule authority | Scheduled-app gate | Production approved scheduler integration is not demonstrated. | Session flow uses local contracts/fixtures; no independent scheduler service is proven. | Integrate the signed/approved scheduler contract and add tamper/freshness tests. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires an external/production scheduler service integration.
GAP-025 | LP-004 | Medium | Commercial authority | Entitlement/credit gates | Session eligibility depends on EN/BI sources that are only partially implemented. | EN-001/EN-002 explicitly lack billing event producers and lifecycle overlays. | Complete BI/EN sources and re-run LP-004 entitlement/weekly/credit regressions. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires the full BI/EN billing lifecycle (product/bundle catalog, checkout, payment gateway) that does not exist in this repo; same root cause as GAP-084/086/088/094/096/097/099.
GAP-026 | AR-001 | Medium | Production data security | Architecture/security | App registry operates on SQLite in active runtime; production Supabase RLS is not exercised. | README states current runtime is local SQLite. | Port/activate Postgres migrations/RLS and run admin authorization integration suite. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires activating Postgres/RLS in production.
GAP-027 | AR-001 | Medium | Commercial integration | AT-AR-001-22 | App soft-delete commercial non-mutation/remediation is not proven against a real billing implementation. | Billing lifecycle requirements are absent. | Add BI/EN integration tests proving historical billing is preserved and no new purchase/use can begin. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a real billing implementation (BI requirements not yet built).
GAP-028 | AR-001 | Low | Distributed concurrency | Idempotency/concurrency | Optimistic/idempotent registry logic is tested in a single local database, not under production multi-instance concurrency. | Current test environment is SQLite. | Add Postgres transactional/concurrency tests for create/update/activate/delete races. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires Postgres multi-instance concurrency testing.
GAP-029 | AN-001 | Medium | Production scheduling | AT-AN-001-09/10 | Daily 00:15 IST production scheduler execution is not demonstrated. | Repository contains job logic/admin runs but no verified production scheduler execution evidence. | Configure Vercel Cron or chosen scheduler, authenticate it and add runbook/monitoring checks. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires configuring the production scheduler (Vercel Cron) and its authentication.
GAP-030 | AN-001 | Medium | Machine identity | Internal authorization | Analytics internal service authentication is not using the frozen AU-004 managed public-key identity. | Current app/service principal architecture still contains shared-secret HS256 assertions. | Move scheduler/service authentication to AU-004 Ed25519 managed principals. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-launch/principal.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - AU-004 Ed25519 managed machine identity; AN-001 scheduler/contributor platform-service principals now sign with EdDSA, verified against a stored public key, no shared secret.
GAP-031 | AN-001 | Low | Production storage | RLS/retention | Anonymous-buffer retention behavior is not validated on the production Postgres path. | Current runtime is SQLite. | Run retention/reconciliation/purge tests on Supabase/Postgres before production certification. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires production Postgres to validate retention/purge behavior.
GAP-032 | AR-002 | High | Provider integration | AT-AR-002-01/02 | Deployment provider discovery/project picker is not proven against live Vercel provider APIs. | Repository has deployment service primitives but no verified provider-connected production flow. | Implement/verify DeploymentProvider Vercel adapter, project discovery and ownership validation. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires live Vercel provider API access.
GAP-033 | AR-002 | High | Repository provenance | AT-AR-002-03/04 | Provider project ↔ repository ownership/repository binding is not proven end-to-end. | Static services exist without live provider/source-control provenance evidence. | Verify provider team ownership and exact GitHub repository binding before activation. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires live provider/source-control provenance (Vercel + GitHub).
GAP-034 | AR-002 | High | CI-only release creation | AT-AR-002-09 | CI-only immutable release creation is not fully enforced by an external CI principal. | No complete connected CI release publication path was established in the audited runtime. | Require managed CI service identity and deny browser/admin release creation. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a connected external CI identity/pipeline.
GAP-035 | AR-002 | High | Artifact immutability | AT-AR-002-10/11/12 | Build-once immutable artifact promotion across environments is incomplete. | Release/deployment records exist, but provider artifact digest promotion is not demonstrated. | Bind release to commit+artifact digest and promote the same artifact to staging/production. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires live provider artifact-digest promotion (Vercel).
GAP-036 | AR-002 | High | Manifest validation | AT-AR-002-07/08 | Release manifest identity/path validation is not proven as a mandatory pipeline gate. | No complete CI manifest attestation path was verified. | Require signed/validated manifest with app_key, safe paths and contract versions before verification. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a connected external CI manifest-attestation pipeline.
GAP-037 | AR-002 | High | Compatibility gate | AT-AR-002-36/37 | Represented progress schema compatibility and destructive-migration blocking are incomplete. | PR-001 migration requirement is frozen in v45 but not implemented in the repository. | Implement PR-001 schema registry/migration path and make AR-002 promotion depend on it. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - PR-001 progress schema registry (src/lib/progress-schema-registry/service.ts) gate wired into AR-002's approveProduction via assertReleaseSchemaCompatibility; a release with no forward+rollback migration path from an in-use schema version cannot promote.
GAP-038 | AR-002 | High | Deployment window | AT-AR-002-38/39 | Advance-window/drain orchestration is not proven against a real provider deployment. | Central block logic exists, but no provider-connected scheduled production execution evidence. | Enforce >=60-minute scheduled window and T-60 drain with provider operation idempotency. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a real provider-connected scheduled production deployment.
GAP-039 | AR-002 | High | Session safety | AT-AR-002-41 | Zero reserved/active session revalidation at promotion commit is not proven under provider race conditions. | Central counters exist; provider transaction boundary is not connected. | Revalidate session/grant counts immediately before publish and abort/postpone atomically. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires live provider transaction boundaries at promotion time.
GAP-040 | AR-002 | High | Rollback automation | AT-AR-002-42/44 | Safe overrun/rollback publication is incomplete. | No full provider-backed previous-release publication and observation loop was verified. | Implement atomic pointer publish, post-publish observation, rollback and safe overrun state. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a real provider-backed publish/rollback loop (Vercel).
GAP-041 | AR-002 | Medium | Production UI | Admin deployment UX | Admin deployment binding/release/promotion UI is only partial relative to the frozen provider-discovered workflow. | Provider project selection and verification are not fully connected. | Complete provider-backed project picker, release status, production approval and rollback UX. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires the live provider-connected project picker (Vercel) to be connected.
GAP-042 | LA-001 | High | Machine identity | App service authentication | App backend client assertion uses HS256 shared secret rather than AU-004 public-key proof. | createAppClientAssertion/verifyAppClientAssertion explicitly sign/verify HS256 with a secret. | Replace with AU-004 Ed25519 key-pair principal assertions and managed key rotation. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-launch/principal.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - AU-004 Ed25519; app-service client assertions now use a per-principal Ed25519 key pair, no HS256 shared secret.
GAP-043 | LA-001 | High | SC-003 integration | SC-003 amendment | Starting reservation exchange cannot be certified as provisional-only because LA-002 issuance currently creates active grants. | issueInitialAppGrant writes status='active' and broad scopes. | Create provisional bootstrap/grant with only session.usable_launch until SC-003 activation. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-authorization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: session-start grants are now provisional (scope session.usable_launch only) until confirmUsableLaunch atomically activates them to full scope. src/lib/app-authorization/service.ts, src/lib/learning-session/gateway.ts.
GAP-044 | LA-001 | Medium | Cross-domain E2E | AT-LA-001-01/04 | Independent-domain browser/app backend launch has not been exercised against a deployed learning app. | Audited repository is the central platform and local test harness. | Add E2E with an independent app origin validating POST-only launch, cookie isolation and no parent-token leakage. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires an independently deployed learning app to exercise cross-domain E2E.
GAP-045 | LA-001 | Medium | Deployment dependency | AT-LA-001-29..40 | Deployment drain/compatibility behavior depends on incomplete AR-002 provider integration. | Central checks exist but provider publication lifecycle is partial. | Complete AR-002 and run launch regression across drain/publish/rollback windows. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires AR-002's live-provider pieces (see GAP-032-041) to be complete first.
GAP-046 | LA-001 | Medium | Entitlement dependency | EN-002 launch gate | Fresh access gate is only as authoritative as incomplete EN-001/EN-002 billing lifecycle. | Entitlement periods are currently created from caller-supplied events. | Complete verified billing event ingestion and lifecycle overlays, then re-run launch authorization tests. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires the full BI billing event ingestion pipeline.
GAP-047 | LA-001 | Low | Secrets management | Security | App-service shared secrets are environment-resolved rather than managed public keys. | HS256 secret path is still required. | Remove static app service secrets from deployment/runtime once AU-004 is implemented. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-launch/principal.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - AU-004; APP_SERVICE_SECRETS/PLATFORM_SERVICE_SECRETS env-var secret maps removed entirely from the codebase.
GAP-048 | LA-002 | Critical | SC-003 provisional grant | BR3/BR6 + SC-003 amendment | Starting sessions receive an active grant with all APP_API_SCOPES instead of provisional usable-launch-only scope. | issueInitialAppGrant inserts grant status='active'; APP_API_SCOPES includes progress/read/write/complete and heartbeat. | Add grant status=provisional, scope only session.usable_launch, reservation-capped expiry; activate atomically at usable launch. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-authorization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: issueInitialAppGrant creates status='provisional' with only session.usable_launch scope; activateAppGrant upgrades atomically at usable launch. Same fix as GAP-043/089.
GAP-049 | LA-002 | High | Machine identity | Dual credential | Fresh app assertion is HS256 shared-secret based, not AU-004 managed Ed25519 identity. | verifyAppClientAssertion resolves a shared secret and restricts algorithms to HS256. | Migrate app client assertions to AU-004 public-key verification and key rotation. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-launch/principal.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - AU-004; LA-002 fresh app assertion now verified via the principal's stored Ed25519 public key.
GAP-050 | LA-002 | Medium | Scope model | No recurring heartbeat | Approved scope list still includes session.heartbeat despite v45 moving runtime timing local and eliminating recurring heartbeat. | APP_API_SCOPES contains session.heartbeat. | Remove heartbeat scope/endpoint from the normal app grant unless a non-periodic, explicitly approved use remains. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-authorization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: session.heartbeat renamed to session.usable_launch across APP_API_SCOPES and the three routes that used it (usable-launch/disconnect/resume) - reflects the actual non-periodic use, no recurring heartbeat remains.
GAP-051 | LA-002 | High | Pre-activation authorization | SC-003 amendment | Current live-grant check treats starting sessions as authorized normal grant state. | assertLiveGrant accepts learner session status 'starting'. | For starting state, accept only a provisional grant at usable-launch endpoint; reject progress/completion/renewal. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-authorization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: assertLiveGrant now rejects a provisional grant once the session is no longer 'starting'. src/lib/app-authorization/service.ts.
GAP-052 | LA-002 | Medium | SDK integration | Backend cache/renewal | No independently deployed learning-app backend SDK/cache/renewal integration is proven. | Central token service exists, but consumer-side implementation is outside the audited repo. | Publish/consume SDK and add contract E2E for silent renewal, revocation and no-browser-token guarantees. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform/out-of-repo: requires a learning-app backend SDK maintained outside this repository.
GAP-053 | LA-002 | Medium | Production key rotation | AT-LA-002-37 | Access-token verification supports multiple keys from environment configuration, but production managed-key rotation is not operationally proven. | APP_ACCESS_VERIFY_KEYS is environment JSON, not a managed key lifecycle service. | Implement managed signing-key rotation/runbook and automated overlap/removal tests. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-authorization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires an operational managed-key rotation runbook.
GAP-054 | LA-003 | High | Progress migration | AT-LA-003-36/37 + PR-001 | Frozen PR-001 per-row schema migration/rollback path is not implemented end-to-end. | v45 requires represented schema compatibility and rollback-safe migration; no complete PR-001 implementation was found. | Implement schema registry, deterministic migrators, compatibility gates and rollback read/migration. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - PR-001 schema registry: deterministic declarative (rename/default/drop) migrators walked step-by-step, plus the AR-002 forward/rollback compatibility gate.
GAP-055 | LA-003 | High | Unsaved recovery | PR-002 amendment | Pending meaningful-progress capsule/original-device recovery contract is not implemented in a learning-app runtime. | SC-001 browser runtime is absent. | Implement signed/bound local pending capsule with server-version/hard-expiry checks and one-time recovery. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001's prepareResume implements the signed/bound (HMAC over a device-local key that never leaves IndexedDB) pending capsule with hard-expiry and server-progress-version checks, one-time recovery.
GAP-056 | LA-003 | Medium | Progress summary | PR-003 amendment | Standard app-owned progress summary fields are not demonstrated as validated persisted/displayed contract. | Core progress stores opaque state; newer PR-003 summary requirement was frozen after much of this implementation. | Add latest acknowledged current level, efficiency stars, milestone and next destination contract. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - PR-003 standard app-owned progress summary contract (current level, efficiency stars, milestone, next destination) added to saveCheckpoint/completeLesson, validated and persisted on learner_app_progress.progress_summary_json.
GAP-057 | LA-003 | Medium | Client checkpoint behavior | Checkpoint cadence | Server APIs exist, but meaningful/change-gated client checkpoint emission is not implemented in a learning app. | No SC-001 runtime SDK is present. | Implement checkpoint policy in SDK and ensure question/click activity does not trigger DB writes. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001's checkpointIfDue implements the five-minute change-gated checkpoint; ordinary interaction (clicks/navigation) never reaches a DB write, proven by a test spanning a simulated 45-minute session.
GAP-058 | LA-003 | Medium | Production database | Architecture | Progress persistence runs on local SQLite rather than active Supabase/Postgres. | README explicitly states current runtime is SQLite. | Activate Postgres path, constraints/RLS and load/concurrency tests. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires activating production Postgres/Supabase for progress persistence.
GAP-059 | LA-003 | Medium | Release coupling | AR-002 dependency | Progress schema compatibility is not a fully enforced production release promotion gate. | AR-002/PR-001 are incomplete. | Block release promotion unless all represented progress schemas have safe forward/rollback paths. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - same AR-002 promotion gate as GAP-037 (assertReleaseSchemaCompatibility blocks promotion without a safe schema migration path).
GAP-060 | LA-004 | Critical | Requirement regression | LP-004/SC-001 amendment | Automatic repeated-interruption completion remains an allowed server finalization reason. | finalizeSessionAutomatically accepts repeated_interruption_after_threshold. | Remove the reason and associated trigger; use hard expiry and explicit valid end reasons only. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/session-finalization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: same fix as GAP-019/080 - repeated-interruption auto-completion removed.
GAP-061 | LA-004 | High | Local progress recovery | PR-002 | Completion does not have the full browser pending-progress capsule/recovery handshake required by later frozen progress rules. | SC-001 runtime is not implemented in the audited repo. | Implement final pending-state flush/retry and original-device bounded recovery before final completion. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001's prepareResume/checkpointIfDue give LA-004 completion a real local pending-capsule flush/retry and original-device-bounded recovery path.
GAP-062 | LA-004 | Medium | Progress summary integration | PR-003 | Finalization does not prove update/display of the standardized app-owned progress summary. | Core final_progress_version is enforced, but PR-003 common summary contract is not complete. | Validate/store summary in the acknowledged progress checkpoint before completion. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/session-finalization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - PR-003 summary is surfaced again at session finalization (finalProgressSummary in the finalizeLearnerSession response).
GAP-063 | LA-004 | Medium | Production app E2E | Return/logout UX | App-side safe return screen/cookie cleanup is not tested across an independently deployed learning app. | Central finalization exists; consumer app UI/runtime is outside this repository. | Add cross-domain E2E for complete → revoke → return, including stale-token denial. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires an independently deployed learning app for cross-domain E2E.
GAP-064 | LA-004 | Medium | Production database | Transactions/outbox | Finalization/analytics atomicity is validated locally, not on production Postgres/outbox infrastructure. | Current active DB is SQLite. | Run fault-injection and idempotency suite on Postgres with real outbox boundaries. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires production Postgres/outbox infrastructure.
GAP-065 | AU-001 | High | Machine principal | AU-004 dependency | App-service principal authentication does not use the frozen AU-004 public-key identity contract. | Current app assertion is HS256 shared-secret based. | Implement AU-004 and make AU-001 app-service context derive only from verified managed principals. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-launch/principal.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - AU-004; AU-001's app-service context now derives only from a verified Ed25519-signed managed principal.
GAP-066 | AU-001 | Medium | Distributed policy runtime | Authorization context | Authorization policy/action state is stored/evaluated in the local database runtime. | Current active runtime is SQLite. | Move canonical policy/action data to production Postgres and validate multi-instance consistency. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/authorization/modes.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires moving canonical policy data to production Postgres.
GAP-067 | AU-001 | Medium | Deployment authorization | AT-AU-001-41..48 | Deployment policy decisions depend on incomplete AR-002 provider lifecycle. | Canonical actions exist, but provider-connected schedule/promote/rollback flow is partial. | Complete AR-002 and re-run deployment authorization/messaging regressions. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/authorization/modes.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires AR-002's live-provider pieces (see GAP-032-041) to be complete first.
GAP-068 | AU-001 | Medium | Transaction reauthorization | AT-AU-001-10/11 | Production TOCTOU/locked reauthorization is not proven under Postgres concurrency. | Current tests run against SQLite. | Add serializable/row-lock Postgres race tests for sensitive mutations. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires Postgres serializable/row-lock concurrency testing.
GAP-069 | AU-001 | Low | External static scans | Architecture | No evidence that independent learning-app repositories are scanned for direct DB/service-role credentials. | Central repo can enforce its own code but cannot certify downstream app repos. | Add CI policy checks/SDK contract scans to each learning-app repository. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform/out-of-repo: requires CI policy scans on each independent learning-app repository.
GAP-070 | AU-002 | Critical | WebAuthn | AT-AU-002-03/04 | No WebAuthn learner-passkey registration/options/verification implementation was found. | Learner mode infrastructure exists but no IA-004 credential/challenge service is present. | Implement IA-004 WebAuthn end-to-end before enabling learner mode. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/authorization/modes.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - IA-004: full WebAuthn registration/authentication implementation (@simplewebauthn/server) with real ECDSA ceremonies, tested via a from-scratch virtual authenticator, not mocks.
GAP-071 | AU-002 | Critical | Trust boundary | Learner unlock | activateLearnerMode trusts a caller-supplied boolean passkeyVerified. | Function only checks if passkeyVerified is true; it does not verify a credential assertion itself. | Pass a verified server-side IA-004 assertion result/credential context, not a free boolean. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/authorization/modes.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - activateLearnerMode already took a verificationReceiptId (not a boolean); IA-004 now supplies the real verifier that produces that receipt only after genuine WebAuthn verification.
GAP-072 | AU-002 | High | Passkey challenge lifecycle | Security | No 5-minute single-use hashed WebAuthn challenge/replay protection is implemented. | No credential/challenge store was found for IA-004. | Add challenge issuance, hash-only storage, expiry and replay prevention. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/authorization/modes.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - IA-004: 5-minute single-use hashed (never raw) WebAuthn challenges in webauthn_challenges, consumed exactly once.
GAP-073 | AU-002 | High | Credential lifecycle | AT-AU-002-23 | No real learner passkey credential registry/revocation path is implemented. | Context revocation by credential ID exists, but credential authenticity/lifecycle source is absent. | Implement credential records, labels, active/revoked states, and reauth-protected management. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/authorization/modes.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - IA-004: learner_passkey_credentials registry with label, active/revoked state, sign-counter clone detection, and reauth-protected revocation that also tears down any active learner-mode context bound to the credential.
GAP-074 | AU-002 | High | Unsupported/missing passkey UX | Learner mode UX | No supported-platform/missing-passkey locked learner screen and enrollment flow is implemented end-to-end. | No IA-004 UI/routes were found. | Implement locked learner UX with explicit enroll requirement and no fallback learner password/PIN. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - IA-004: locked-learner enrollment/unlock UI (src/components/learner-mode/passkey-unlock.tsx) with explicit browserSupportsWebAuthn() feature detection and no password/PIN fallback.
GAP-075 | AU-002 | Medium | Logout invalidation | AT-AU-002-21 | Parent sign-out clears the cookie but does not explicitly revoke persisted learner unlock contexts in the shown signOut action. | signOutAction calls clearSessionCookie only. | Revoke learner contexts for the parent session/device on logout, then clear cookie. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/app/(auth)/actions.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Already resolved prior to this audit pass (commit 89efe0a) - signOutAction calls revokeLearnerContextsForSession before clearing the cookie. src/app/(auth)/actions.ts:180-185. Verified 2026-08-08; no further action needed.
GAP-076 | AU-002 | Medium | Production session binding | Device/session context | Mode binding is implemented against local session IDs and SQLite, not verified on production Supabase session lifecycle. | Current active auth is built-in local JWT. | Validate nested context expiry/revocation against production parent sessions and multi-device cases. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires validating against production Supabase parent-session lifecycle.
GAP-077 | SC-001 | Critical | Browser persistence | AT-SC-001-01 | No actual IndexedDB runtime implementation is present in the audited repository. | Central server code contains contracts but not the learning-app browser runtime. | Implement versioned IndexedDB runtime in the shared learning-app SDK. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001 browser runtime SDK: real IndexedDB implementation (src/lib/session-runtime-sdk/idb.ts) in the shared learning-app SDK.
GAP-078 | SC-001 | High | Envelope verification | AT-SC-001-02 | Browser-side signed session-envelope verification is not demonstrated in a real learning app. | Consumer runtime implementation is absent. | Implement and E2E test envelope verification before local runtime creation. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - session envelope switched from HS256 to EdDSA specifically so the browser SDK's createRuntime can verify it with only the Ed25519 public key, before any local runtime is created.
GAP-079 | SC-001 | High | Single-tab ownership | AT-LP-004-36 / SC-001 | Web Locks/BroadcastChannel single-owner-tab control is absent. | No browser runtime package implementing tab ownership was found. | Add single-owner tab lease/coordination and pause non-owner tabs. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001's claimOwnerTab: Web Locks single-owner-tab lease plus BroadcastChannel coordination, tested against a mocked LockManager for real acquire/contend/release semantics.
GAP-080 | SC-001 | Critical | Requirement regression | AT-SC-001-24 / LP-004-37 | Server still retains the old repeated-interruption completion path. | finalizeSessionAutomatically includes repeated_interruption_after_threshold. | Delete old threshold rule and associated server/client behavior. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/session-finalization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: same fix as GAP-019/060 - repeated-interruption auto-completion removed.
GAP-081 | SC-001 | High | Pending recovery | PR-002 | One pending meaningful-progress capsule with original-device bounded recovery is absent. | No browser-local runtime implementation was found. | Implement capsule signing/binding, hard-expiry check, server-version comparison and one-time recovery. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - same pending-capsule mechanism as GAP-055 (signing/binding, hard-expiry check, server-version comparison, one-time recovery).
GAP-082 | SC-001 | High | Runtime migration | AT-SC-001-28 / PR-001 | Browser runtime version migration is not implemented/proven. | No client runtime migration registry/package was found. | Add versioned local runtime migrators and unsupported-version fail-closed behavior. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001 migrations.ts: versioned local runtime migrators with fail-closed behavior on an unrecognized future version, exercised end-to-end.
GAP-083 | SC-001 | Medium | Bandwidth certification | AT-SC-001-30 | Zero periodic platform DB/API calls over a real 45-minute app session is not measured end-to-end. | No deployed learning-app runtime test is present. | Add network/DB instrumentation E2E proving start/read/meaningful writes/finalize only. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - test proves zero network/platform-DB calls occur across a simulated 45-minute session absent a due+dirty checkpoint (only meaningful changes ever produce a sync call).
GAP-084 | SC-002 | High | Billing authority | AT-SC-002-01..08 | Recurring eight-credit allocation can be created from a caller-supplied paid-cycle event rather than a verified BI billing event. | EN-001 comment explicitly says no BI producer exists and caller supplies the full event. | Only accept authenticated, idempotent BI-005 paid-cycle events from the billing service. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a real BI-005 billing event producer/gateway.
GAP-085 | SC-002 | High | Calendar correctness | AT-SC-002-05 | Rollover expiry is computed by adding prior cycle duration in milliseconds, which can break Jan-31/short-month anchor restoration. | batchExpiresAt = periodEnd + (periodEnd - periodStart). | Compute expiry from subscription billing anchor/calendar-cycle boundaries with clamp-and-restore semantics. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: standard-credit batch expiry now computed via calendar-anchor month arithmetic (addCalendarMonthsClamped/calendarMonthsBetween), not raw millisecond duration - fixes drift across months of different lengths. src/lib/entitlement-cycle/service.ts.
GAP-086 | SC-002 | Medium | Bundle authority | AT-SC-002-02 | Per-app bundle allocations depend on caller-supplied appIds instead of an immutable verified product-version snapshot. | No bundle catalog exists; appIds are supplied in ApplyPaidCycleInput. | Resolve app set from immutable paid-cycle product snapshot produced by billing/catalog service. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a product/bundle catalog service.
GAP-087 | SC-002 | Medium | Production concurrency | Reservation/consumption | Credit/week reservation atomicity is not certified on Postgres under multi-instance races. | Current runtime/test DB is SQLite. | Run serializable/locking concurrency tests on Supabase/Postgres. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires Postgres multi-instance concurrency testing.
GAP-088 | SC-002 | Medium | Parent/learner UI | Allowance summary | Production learner/parent balance/expiry/catch-up presentation is not fully integrated with billing-backed entitlements. | Central data exists but BI/EN lifecycle is partial. | Complete UI integration after authoritative billing lifecycle is available. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires the BI/EN billing lifecycle to be complete.
GAP-089 | SC-003 | Critical | Provisional authorization | LA-002 amendment | Reservation exchange currently creates an active broad-scope grant rather than provisional usable-launch-only authorization. | LA-002 issueInitialAppGrant inserts active status/all scopes. | Implement provisional grant and atomic provisional→active transition at usable launch. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-authorization/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: same fix as GAP-043/048 - provisional-until-usable-launch grant lifecycle.
GAP-090 | SC-003 | High | Browser runtime handshake | Usable launch | Real browser runtime initialization → backend usable-launch handshake is not implemented end-to-end. | No learning-app browser runtime package is present. | Implement SDK boot, IndexedDB initialization and backend usable-launch callback before consuming funding. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - SC-001 browser runtime SDK provides the real SDK-boot/IndexedDB-initialization half of the handshake; the app backend's own usable-launch callback into the already-real POST usable-launch route is the out-of-repo half, same boundary as GAP-052.
GAP-091 | SC-003 | High | Machine identity | AU-004 | Usable-launch dual proof relies on shared-secret app assertion rather than AU-004 managed key identity. | App client assertion is HS256. | Migrate app principal authentication to Ed25519 managed keys. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/app-launch/principal.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - AU-004; SC-003 usable-launch dual proof now uses Ed25519 app-service assertions.
GAP-092 | SC-003 | High | Progress migration gate | PR-001 | Required progress/runtime migration before usable launch is incomplete. | PR-001 is frozen in v45 but no full migration engine is implemented. | Run required progress/runtime migration during reservation before funding consumption and block on failure. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - PR-001's migrateLearnerProgressToReleaseSchema wired into confirmUsableLaunch, running before funding consumption and blocking (leaving funding untouched) if no migration path exists.
GAP-093 | SC-003 | Medium | Effective access lifecycle | EN-002 | Fresh entitlement check exists, but its lifecycle model is incomplete and mishandles resume after paid-end. | evaluateAccessFresh is period-based and lacks completed BI/EN lifecycle overlays. | Complete EN-002 lifecycle model and add SC-003 freshness regressions. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-access/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires BI/EN-003 lifecycle event producers (grace/cancellation) that do not exist; same root cause as GAP-097/103/104.
GAP-094 | EN-001 | Critical | Event authenticity | Authority | Paid-cycle event is supplied by the caller with no implemented BI producer/authenticity boundary. | Source comment states future billing webhook/manual/test caller supplies the full event. | Accept only verified BI billing lifecycle events with service identity, version and replay protection. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a real BI billing event producer with service-identity/replay protection.
GAP-095 | EN-001 | High | Ownership validation | Source binding | applyPaidCycle checks that learner exists but does not verify that assignedLearnerId is owned by purchaserParentId. | Code selects learner by id only before creating entitlement cycle. | Verify learner.owner_parent_id == purchaserParentId under lock before materialization. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: applyPaidCycle now verifies learner.owner_parent_id == purchaserParentId before materializing an entitlement cycle. src/lib/entitlement-cycle/service.ts.
GAP-096 | EN-001 | High | Product authority | Immutable bundle snapshot | appIds/productVersion are caller-supplied because no authoritative product/bundle catalog snapshot exists. | Code comment explicitly says no bundle catalog exists to re-derive it. | Consume immutable product-version app snapshot from billing/catalog event; reject arbitrary app lists. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a product/bundle catalog service.
GAP-097 | EN-001 | High | Lifecycle overlays | Grace/cancellation/catalog | Grace, cancellation and catalog-version lifecycle overlays are intentionally not implemented. | Source comment states these rules are intentionally omitted because no producer exists. | Implement verified EN-003/BI event handling for cancellation, reversal, grace and source version changes. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires BI/EN-003 lifecycle event producers (grace/cancellation) that do not exist.
GAP-098 | EN-001 | High | Calendar expiry | Credit rollover | Standard credit batch expiry uses duration arithmetic rather than subscription anchor boundaries. | cycleLengthMs is added to periodEnd. | Use billing-anchor calendar calculations for exact following-cycle boundary. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: same fix as GAP-085 - calendar-anchor-based expiry.
GAP-099 | EN-001 | High | Subscription validation | Commercial source | Subscription/product/paid-provider state is not validated against authoritative BI records before creating periods. | Input IDs are trusted beyond app/learner existence checks. | Resolve and lock authoritative subscription/product/paid cycle records before entitlement writes. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires authoritative BI subscription/product/payment records.
GAP-100 | EN-001 | Medium | Service authorization | AU-004 | Entitlement cycle application is not bound to the frozen managed machine-principal model. | AU-004 is not implemented; service functions can be called by future/manual caller. | Expose only internal authenticated endpoint using managed service identity and exact action authorization. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - AU-004; the apply-paid-cycle/evaluate-access internal routes already required requireInternalService, now backed by verified Ed25519 managed principals instead of an HS256 shared-secret scheme.
GAP-101 | EN-002 | Critical | Resume lifecycle | AT-EN-002-11 | Fresh access evaluation denies resume after the entitlement period ends, even for a previously active session that v45 allows to resume until hard expiry. | evaluateAccessFresh uses the same live covering-period requirement for useCase='resume'. | Special-case exact existing session resume: honor original entitlement binding through hard expiry without creating new entitlement. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-access/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved 2026-08-08: evaluateAccessFresh special-cases useCase='resume' to honor the session's original entitlement binding (persisted at Start) through hard expiry, instead of re-checking a live covering period. Wired into resumeLearnerSession. src/lib/entitlement-access/service.ts, src/lib/learning-session/gateway.ts.
GAP-102 | EN-002 | High | Checkout overlap | AT-EN-002-13..23 | Checkout overlap rejection, activation race, paid-overlap incident and case path are not implemented. | No BI checkout/payment flow exists in repository. | Implement overlap check at intent and recheck at payment activation with deterministic incident handling. | https://github.com/SridharVoleti/babystepsindia/blob/master/README.md | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a BI checkout/payment flow to exist at all.
GAP-103 | EN-002 | High | Grace overlay | AT-EN-002-04 | Approved grace access state is not represented by evaluateAccessFresh. | AccessDecision state supports only active/inactive; no approved_grace overlay. | Add verified grace overlay from billing lifecycle without creating a new standard allocation. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-access/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a BI/EN-003 grace-lifecycle producer.
GAP-104 | EN-002 | High | Cancellation lifecycle | AT-EN-002-05/06 | Cancellation/reversal lifecycle is not represented beyond static entitlement periods. | EN-001 explicitly omits cancellation overlays; EN-003 producer is absent. | Apply verified lifecycle events and recompute effective access/version at paid-end/cancel/reverse boundaries. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires a BI/EN-003 cancellation/reversal producer.
GAP-105 | EN-002 | High | Source authenticity | Authority | Effective access is only as trustworthy as entitlement periods created from caller-supplied paid-cycle input. | EN-001 does not currently verify a billing producer or purchaser ownership. | Fix EN-001 authority boundary before treating EN-002 as security-authoritative. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-cycle/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: same root cause as GAP-094 - requires a real BI billing event producer.
GAP-106 | EN-002 | Medium | Cache contract | AT-EN-002-35/36 | Bounded launcher cache semantics are not implemented as a clear server cache contract. | evaluateAccessFresh always reads DB; no explicit nearest-boundary cache layer was identified. | Implement optional bounded launcher cache that never authorizes Start and expires by nearest entitlement/app boundary. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-access/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Resolved | Resolved - evaluateAccessForLauncher (src/lib/entitlement-access/launcher-cache.ts): a bounded, read-only cache for launcher/home-screen display only, expiring at the sooner of a 60s TTL or the decision's own nearest entitlement/app boundary; never consulted by Start/exchange/usable-launch/resume.
GAP-107 | EN-002 | Medium | Lifecycle versioning | AT-EN-002-34 | effective_version bumps only when period/role source-set hash changes, not necessarily on all lifecycle state changes such as grace/cancel. | source_set_hash contains only period IDs and roles; missing lifecycle overlays cannot bump it. | Include authoritative lifecycle source/version in effective decision version and invalidate caches on every relevant event. | https://github.com/SridharVoleti/babystepsindia/blob/master/src/lib/entitlement-access/service.ts | Babysteps_Platform_Requirements_v45.xlsx | Deferred | Deferred - platform: requires EN-003 lifecycle overlays (grace/cancel) driven by a BI producer that does not exist; same root cause as GAP-093/097/103/104.

## Scoring & Scope
Scoring Method, Scope & Audit Caveats
Item | Definition |  |  | Source | Value | Notes
Full Match | 1.0 point — inspected implementation materially satisfies the frozen behavior/constraint. |  |  | Requirements | Babysteps_Platform_Requirements_v45.xlsx | Frozen acceptance source
Partial Match | 0.5 point — core behavior exists but production runtime, dependency, edge case or contract is incomplete. |  |  | Repository | https://github.com/SridharVoleti/babystepsindia | Audited codebase
Missing / Contradicted | 0 points — required behavior is absent or implementation conflicts with v45. |  |  | Branch | master | Default branch
Formula | Match % = (Full + 0.5 × Partial) / Acceptance Criteria or approved acceptance-test count. |  |  | HEAD | 517e3cf3ef141908679742ef2abb60dd93b32400 | Audited repository state
Audit type | Static repository audit against v45. It is not a production certification or a substitute for executing the complete acceptance suite. |  |  | Runtime note | README: local SQLite + built-in auth | Major recurring production-contract deduction
Gap coverage | Gap Register lists every distinct gap identified during this static review; shared architectural gaps are repeated where they materially reduce a requirement score.
Included Requirement | Why Included | Implementation Signal | Excluded / Not Scored
IA-001/002/003 | Explicit auth/profile/security implementation and tests | README, routes, repos, migrations | IA-004 — no WebAuthn implementation found
LP-001/002/004 | Explicit learner/session services and tests | Learner routes/repos, session services, migrations | New BB-10 launcher requirements — no explicit v45 implementation slice at audited HEAD
AR-001 | Explicit app registry implementation/tests | Admin app registry services/migrations | —
AN-001 | Explicit analytics implementation/tests | Analytics buffer/jobs/admin routes | Other analytics requirements not implemented
AR-002 | Meaningful deployment primitives exist | Deployment services/routes/tests | Scored as Partial, not as completed
LA-001/002/003/004 | Explicit launch/auth/progress/finalization services/tests | App launch/grant/progress/finalization modules | —
AU-001/002 | Explicit policy/mode services/tests | authorization/modes and action catalog | AU-004 — machine identity contract not implemented
SC-001/002/003 | Explicit runtime/credits/start contracts and server pieces | Session/credit/start services/tests | SC-001 browser SDK itself remains partial
EN-001/002 | Explicit entitlement-cycle/access services/tests | entitlement-cycle/access modules | EN-003 lifecycle events not implemented
Billing BI-* / Progress PR-* | Not scored | No complete implementation slice found | These appear as dependencies/gaps where they reduce an implemented requirement's match