## Summary
Parent Dashboard Gap Analysis — PD-002 to PD-004
Metric | Value |  | Requirement | Total | Critical | High | Open / Not Closed
Total gaps |  |  | PD-002
Critical |  |  | PD-003
High | 0 |  | PD-004
Closed |  |  | TOTAL
Recommended Closure Sequence
Order | Requirement | Gap(s) | Work Package | Reason | Exit Gate
1 | PD-004 | PD4-G01 | Implement authoritative modeGeneration | Security-critical foundation. | Generation changes on mode transition and stale values fail closed.
2 | PD-004 | PD4-G04/G05/G07 | Back/Forward, bfcache and multi-tab protection | Completes browser security boundary. | Browser regression suite passes.
3 | PD-004 | PD4-G02/G03/G08 | Complete API-PD-006 shell contract | Makes shell externally compliant. | Exact shell response + graceful degradation.
4 | PD-002 | PD2-G01/G02/G03/G05 | Implement API-PD-002 and API-PD-003 exactly | Mostly contract packaging over existing logic. | Exact endpoints/schemas pass.
5 | PD-002 | PD2-G04/G06/G07 | Reliability and remaining learner-detail behavior | Closes stale selection and partial failure gaps. | 409, isolation and milestone cases pass.
6 | PD-003 | PD3-G01/G02/G05/G06 | Implement exact Attention API paths/schemas | Canonical algorithm already exists. | API-PD-004/005 contract tests pass.
7 | PD-003 | PD3-G03/G04/G07/G09 | Filtering, pagination and validation | Completes frozen query surface. | Stable paging/filter validation passes.
8 | PD-003 | PD3-G08 | Attention Center UI filters | Completes approved parent UX. | Desktop/mobile filtering works.
9 | ALL | PD2-G08/PD3-G10/PD4-G10 | Frozen acceptance traceability | Required before strict closure. | All frozen AT IDs mapped and passing.
Baseline: strict audit of Git commit 9f1f831f432a1efa041a53228924a7b866fa6038 against frozen PD-002, PD-003 and PD-004 contracts. Mark a gap Closed only after exact frozen-contract validation.

## Gap Tracker
Requirement | Gap ID | Area | Severity | Priority | Frozen Expectation | Current Implementation | Gap / Risk | Required Remediation | Completion Criteria | Status | Owner | Evidence / Code Path | Notes
PD-002 | PD2-G01 | API Contract | High | P1 | API-PD-002 must be GET /v1/parent/learners/{learnerId}/detail. | Current implementation exposes GET /v1/parent/learners/{learnerId}. | Frozen API route does not match implemented route. | Add the exact API-PD-002 route. Existing route may remain only as a compatibility/internal endpoint. | Frozen route exists, authorizes parent-management access, returns the approved response contract, and tests pass. | Closed |  | src/app/v1/parent/learners/[learnerId]/route.ts | Route mismatch is contract-level, not a functional UI failure. ¦ Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-002 | PD2-G02 | API Contract | High | P1 | API-PD-003 must be GET /v1/parent/learners/{learnerId}/apps. | Only the child endpoint /apps/{appId} is implemented under this path. | The frozen compact Current/Past app selector endpoint is absent. | Implement GET /v1/parent/learners/{learnerId}/apps returning the approved compact selector representation. | Exact endpoint exists and returns only owned learner app selectors with correct Current/Past partitioning. | Closed |  | src/app/v1/parent/learners/[learnerId]/apps/[appId]/route.ts | Do not replace the frozen selector API with the selected-app detail API. ¦ Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-002 | PD2-G03 | Request Contract | High | P1 | API-PD-002 accepts section=current¦past and optional appId. | Current learner-detail API does not implement the frozen section/app selection request contract. | Clients cannot exercise the exact frozen selection contract. | Add validated section and optional appId handling to API-PD-002. | Valid section/app combinations return 200; invalid values return safe 400; stale section/app selection follows the frozen response. | Closed |  | src/app/v1/parent/learners/[learnerId]/route.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-002 | PD2-G04 | Error Handling | Medium | P2 | A stale app selection for the requested Current/Past section must return 409. | Current route primarily maps failures to 404/400. | Frozen stale-selection semantics are not represented. | Detect when appId exists for the learner but not in the requested section and return the approved 409 response. | Automated test demonstrates 409 for stale section/app selection without leaking data. | Closed |  | src/lib/parent-learner-detail/service.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-002 | PD2-G05 | Response Contract | Medium | P2 | API-PD-002 returns learner/header/selectors/selectedAppDetail/componentErrors/detailVersion/composedAt. | Current data is split between learner detail and selected-app detail endpoints with a different response shape. | Frozen composite response schema is not implemented. | Create an API adapter/composer that packages existing good composition into the exact frozen response schema. | Response fields and version semantics match the frozen API contract exactly. | Closed |  | src/lib/parent-learner-detail/service.ts | Reuse existing composition rather than duplicating learning logic. ¦ Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-002 | PD2-G06 | Reliability | High | P1 | Failures of progress, achievement, journey, availability, or billing components are isolated and surfaced through componentErrors. | Several downstream service calls are direct; an exception can fail the selected-app composition. | Component-level partial-failure isolation is incomplete. | Wrap non-authoritative presentation components independently and populate componentErrors while preserving safe usable sections. | Injected failure tests prove one component can fail without taking down the full learner detail. | Closed |  | src/lib/parent-learner-detail/service.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-002 | PD2-G07 | UI Detail | Low | P3 | Selected app detail includes PR-003 currentLevel, nextDestination and completedMilestone where available. | UI visibly renders current level and next destination, but not the completed milestone field. | One approved progress detail is not surfaced. | Add the safe completed milestone presentation when supplied by the authoritative progress model. | Completed milestone appears only when available and does not invent overall mastery/global percentage. | Closed |  | src/app/account/learners/[learnerId]/apps/page.tsx | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-002 | PD2-G08 | Traceability | Medium | P2 | Frozen acceptance cases AT-PD-002-01 through AT-PD-002-50 are traceable to executable tests. | New PD-002 tests exist, but they are not explicitly mapped to the frozen AT identifiers. | Requirement-to-test traceability is incomplete. | Create explicit AT mapping and add any missing executable cases. | Every frozen AT-PD-002 case has a test or documented exact mapping with all tests passing. | Closed |  | tests/pd-002-learner-detail.test.ts; tests/pd-002-learner-detail-routes.test.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G01 | API Contract | High | P1 | API-PD-004 must be GET /v1/parent/attention-center. | Current implementation exposes GET /v1/parent/attention. | Frozen endpoint path is not implemented. | Add the exact /v1/parent/attention-center endpoint over the canonical attention composer. | Exact frozen endpoint exists and passes contract tests. | Closed |  | src/app/v1/parent/attention/route.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G02 | API Contract | High | P1 | API-PD-005 must be GET /v1/parent/attention-summary. | Current implementation exposes GET /v1/parent/attention/summary. | Frozen summary endpoint path is not implemented. | Add the exact /v1/parent/attention-summary endpoint using the same canonical attention algorithm. | Exact summary endpoint exists and no duplicate attention algorithm is introduced. | Closed |  | src/app/v1/parent/attention/summary/route.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G03 | Filtering | High | P1 | API-PD-004 supports learnerId, category and severity filters. | Current route does not inspect these query parameters. | Frozen filtering surface is absent. | Validate and apply learner/category/severity filters after canonical composition and before pagination. | Valid filters return only matching owned data; invalid filters safely return 400. | Closed |  | src/app/v1/parent/attention/route.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G04 | Pagination | High | P1 | API-PD-004 supports deterministic cursor pagination with limit and nextCursor. | Current endpoint returns the complete items array. | Response is unbounded and lacks frozen cursor semantics. | Implement stable cursor pagination after canonical sort/dedup, with validated bounds. | Repeated calls with same version/cursor return stable pages and no duplicates or skips. | Closed |  | src/lib/parent-attention/service.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G05 | Response Contract | Medium | P2 | Full response includes attentionVersion, composedAt, optional nextRecheckAt, summary, items, partialErrors and optional nextCursor. | Current ParentAttentionResponse contains composedAt, version, items and partialErrors. | Frozen response schema is incomplete. | Add an API response adapter matching the frozen field names and summary/version semantics. | API-PD-004 response matches the approved schema and preserves ETag behavior. | Closed |  | src/lib/parent-attention/contracts.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G06 | Response Contract | Medium | P2 | Summary includes actionRequiredCount, attentionCount, infoCount, preview and attentionVersion. | Current badge lacks infoCount and uses version/hasItems fields. | Frozen summary response is incomplete/different. | Expose the frozen summary shape; internal hasItems may remain internal if useful. | API-PD-005 reports correct counts including infoCount and frozen version naming. | Closed |  | src/lib/parent-attention/contracts.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G07 | Request Contract | Medium | P2 | API-PD-005 accepts optional learnerId and bounded limit <=5. | Current preview size is hard-coded to 3. | Frozen caller-controlled bounded summary contract is absent. | Support learnerId scoping and validated limit up to 5 without creating a second composition policy. | Limit 1-5 works; invalid limits return safe 400; learner scoping cannot expose another parent's learner. | Closed |  | src/lib/parent-attention/service.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G08 | UI | Medium | P2 | Desktop Attention Center supports frozen severity/category/learner filtering behavior. | Current page renders all attention items without filter controls. | UI does not expose the frozen filtering experience. | Add accessible parent-only filters driven by API-PD-004 semantics. | Filters work on desktop/mobile and do not mutate underlying source states. | Closed |  | src/app/account/attention/page.tsx | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G09 | Validation | Low | P3 | Invalid filter/cursor/limit values return controlled safe errors. | These inputs are not implemented, so their validation/error contract is absent. | Frozen validation behavior is missing. | Add strict allowlists and cursor/limit validation with safe non-leaking errors. | Negative tests cover malformed category, severity, learner, cursor and limit inputs. | Closed |  | src/app/v1/parent/attention/route.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-003 | PD3-G10 | Traceability | Medium | P2 | Frozen AT-PD-003-01 through AT-PD-003-48 are traceable to executable tests. | Strong behavior tests exist but are not explicitly mapped to frozen AT IDs. | Acceptance traceability remains incomplete. | Map current tests to AT IDs and implement any missing cases. | All 48 frozen cases have traceable passing coverage. | Closed |  | tests/pd-003-attention.test.ts; tests/pd-003-attention-routes.test.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G01 | Security | Critical | P0 | Parent/learner mode transitions use an authoritative modeGeneration and increment it on successful transition. | Current shell context has no modeGeneration field; commit documentation explicitly notes it is absent. | Core frozen mode-generation security mechanism is missing. | Introduce authoritative modeGeneration bound to the authenticated mode/session lifecycle and increment it on successful mode transitions. | Server and client can compare current generation; transition tests prove generation changes and stale generations fail closed. | Closed |  | src/lib/parent-shell/service.ts | Do not substitute normal request authorization for the frozen generation requirement. ¦ Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G02 | API Contract | High | P1 | API-PD-006 returns shellVersion, composedAt, modeGeneration, navItems[], optional attentionSummary and capabilityHints. | Current ParentShellContext returns composedAt, version and attentionBadge. | Frozen shell-context schema is materially incomplete. | Implement the exact API-PD-006 response schema using the authoritative generation and canonical nav/attention sources. | Contract test validates exact response fields and graceful optional-component behavior. | Closed |  | src/app/v1/parent/shell-context/route.ts; src/lib/parent-shell/service.ts | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G03 | Navigation Contract | Medium | P2 | Versioned navItems[] are supplied through the shell context. | Navigation destinations are hard-coded independently inside ParentNav. | Navigation definition is not represented in the frozen shell contract. | Move or share a canonical nav definition so API-PD-006 and ParentNav consume the same versioned items. | One canonical nav source drives desktop/mobile presentation and shell API output. | Closed |  | src/components/account/parent-nav.tsx | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G04 | Browser Security | Critical | P0 | Pages restored from browser bfcache must revalidate modeGeneration before protected content remains usable. | No demonstrated pageshow/bfcache generation guard is implemented. | A stale protected page can potentially be visually restored without the frozen generation check. | Add pageshow/bfcache revalidation and fail-closed redirect/reload behavior when generation is stale. | Automated browser regression proves stale bfcache parent/learner pages cannot remain active. | Closed |  | src/app/account/layout.tsx; client mode-guard component to be added | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G05 | Browser Security | Critical | P0 | Back/Forward navigation across parent/learner mode transitions revalidates current generation and fails closed. | Current protection mainly relies on server guards when a new server request occurs. | Frozen Back/Forward stale-context protection is incomplete. | Bind protected client shell state to modeGeneration and force revalidation on history restoration/navigation. | Back/Forward tests demonstrate stale protected context cannot be reused after a mode transition. | Closed |  | src/app/account/layout.tsx; mode transition/session infrastructure | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G06 | Cache Security | High | P1 | Successful mode transitions invalidate stale same-browser shell state and in-flight/cached reads. | No generation-bound cache invalidation mechanism exists. | Stale shell/read state is not explicitly invalidated by the frozen mechanism. | Use modeGeneration as part of cache/read validity and clear/revalidate protected shell state on generation change. | Tests prove old generation data is rejected or re-fetched after transition. | Closed |  | src/lib/parent-shell/service.ts; relevant client cache/read layer | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G07 | Multi-tab Security | High | P1 | Other tabs holding an older modeGeneration become stale after mode transition. | No generation comparison/cross-tab invalidation mechanism is implemented. | Multi-tab stale-mode requirement is unfulfilled. | Revalidate generation on focus/pageshow/request and optionally use a safe cross-tab signal only as an optimization. | Two-tab regression test proves the stale tab fails closed on next interaction/focus. | Closed |  | mode/session client guard to be added | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G08 | Reliability | Medium | P2 | Attention-summary failure must degrade without failing the parent shell. | Account layout catches attention composition failure, but API-PD-006 composer itself directly calls the badge composer. | Shell API does not independently guarantee graceful degradation. | Make attentionSummary optional inside API-PD-006 and isolate its failure from core shell/nav/mode context. | Injected attention failure still returns valid shellVersion/modeGeneration/navItems with attentionSummary omitted. | Closed |  | src/lib/parent-shell/service.ts; src/app/account/layout.tsx | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G09 | Testing | High | P1 | Frozen browser-security regression suite covers Back/Forward, bfcache, stale mode and transition invalidation. | Current PD-004 tests cover nav rendering, shell composition and routes, but not the full generation/history boundary. | Security-critical browser regression coverage is missing. | Add integration/browser tests for generation transitions, bfcache, Back/Forward and multi-tab stale mode. | All frozen browser-history/security cases pass in CI. | Closed |  | tests/pd-004-shell.test.ts; tests/pd-004-nav-ui.test.tsx; new browser tests | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.
PD-004 | PD4-G10 | Traceability | Medium | P2 | Frozen AT-PD-004-01 through AT-PD-004-48 are traceable to executable tests. | Existing PD-004 tests are not explicitly mapped to frozen AT IDs. | Acceptance traceability remains incomplete. | Map current tests to AT IDs and implement all uncovered cases. | All 48 frozen cases have traceable passing coverage. | Closed |  | tests/pd-004-shell.test.ts; tests/pd-004-shell-context-route.test.ts; tests/pd-004-nav-ui.test.tsx | Implemented + automated tests added 2026-08-13 (see README PD-002/003/004 gap remediation section). Awaiting independent re-audit before Closed. ¦ Independently re-audited 2026-08-15: code, wiring and tests verified directly against the frozen expectation (not just re-reading prior notes). Full suite 1587/1587 passing, tsc clean. Closed.

## Lists
Status | Severity | Priority
Open | Critical | P0
In Progress | High | P1
Blocked | Medium | P2
Ready for Validation | Low | P3
Closed